## product backlog
PRODUCT BACKLOG ID | PRIORITY | USER STORY ID | user stories | scrum team assigned | status | remark
sprint 1
1 | high | user001 | User Books Appointment | Rishabh team | completed
sprint 2
2 | high | user002 | Doctor Views schedule | Sanket team | completed
sprint 3
3 | medium | user003 | Admin adds new doctor | Arpan team | Pending
4 | medium |  | Patient cancel appointment |  | completed
sprint 4
5 | medium | user004 | Create time slot | Aniket team | Pending
6 | high | user004 | Payment System |  | completed

## sprint backlog 1
USER STORY ID | USER STORY NAME | USER STORY STEP DEFINITION |  |  | ASSIGNED TO | ESTIMATED TIME | ACTUAL TIME | STATUS | REMARKS
|  | AS A<type of user> | I WANT TO <perform some task> | SO THAT I CAN <achieve some goal>
USER001 | User books appoinment | As a Patient | Select date and time for appointment | Succesfully book an appointment | Rishabh | 10hr | 9hr | Completed | Work well
Choose a medical department
Provide personal Information
USER002 | Doctor Views Schedule | Aa a Doctor | Log in to system | View upcoming appointments | Arpan | 11hr | 10hr | Completed | Schedule view clear
|  |  | Access schedule | Plan day accordingly
USER003 | Admins adds new doctor | as a Admin | Enter doctors details | so displayed new doctor in the system | Sanket | 7hr | 7hr | Pending | New Doctor information
|  |  | Set availability | displayed accurate scheduling |  |  |  |  | under review
|  |  | Access appointment details | Review all scheduled appointments
| Patient cancel appointment | as a Patient | Cancel an existing appointment | Free up the time slot |  | 5hr | 6hr | Completed | Cancelation is clear
USER004 | Doctor create time slot | as a Doctor | Set available date and time | Manage availability | Aniket | 15hr | 15hr | Pending | Minor issue with edit
|  |  | Edit time slot | Update availability as needed |  |  |  |  | time slot
|  |  | Block off unavailable slot | Prevent booking during personal time
| Billing Clerk | as a clerk | Handle billing for appointments | Ensure financial transactions are completed |  | 6hr | 8hr | Completed | Billing Process Work
|  |  | send invoices to patients | Request payment for services
|  |  | process insurance claims | facilitate insurance billing

## spring backlog 2
s.no | userstories | user story step | assigned to | estimated hour | status | remark
| call | if network is avialabe it can make calls,
switch to audio video model,